## Sheet1
FY 2023 Budget Funding Sources
Items | Adopted 2022 Budget | 2022 Fund Transfers | Revised 2022 Budget | Actual Spent (Recvd) Year-to-Date | Year to Date Percent of Budget | Straightline Projection End of Year Spent | End of Year Remaining | Projected End of Year Remaining | Projected Carry Over Budget | Grants | Partners & Other Sources | Adopted 2023 Levy | Adopted 2023 Budget | 10-Year Plan CIP Estimate
REVENUES
Plan Implementation Levy | 3640581 | 0 | 3640581 |  | 0% |  |  | 0 | 0 | 0 | 0 | 3821711.137 | 3821711.137
Permit | 25000 | 0 | 25000 | 106956.05 | 427.8% | 106956.05 | -81956.05 | 0 | 0 | 0 | 114000 | 0 | 114000
Grant Income | 71933 | 0 | 71933 | 72875 | 101.3% | 72875 | -942 | 0 | 0 | 0 | 0 | 0 | 0
Investment Income | 30000 | 0 | 30000 | 36267.83 | 120.9% | 36267.83 | -6267.83 | 0 | 0 | 0 | 57000 | 0 | 57000
Past Levies (Carry Overs) | 3355057.5 | 0 | 3355057.5 |  | 0% |  |  | 0 | 3136388 | 0 | 0 | 0 | 3136388
Miscellaneous Income | 0 | 0 | 0 |  | --- |  |  | 0 | 0 | 0 | 0 | 0 | 0
Reimbursements | 0 |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Partner Funds | 272000 | 0 | 272000 |  | 0% |  |  | 0 | 0 | 0 | 100000 | 0 | 100000
TOTAL REVENUE | 7394571.5 | 0 | 7394571.5 | 216098.88 | 2.922% | 216098.88 | 7178472.62 | 0 | 3136388 | 0 | 271000 | 3821711.137 | 7229099.137
EXPENDITURES
Administration
Audit | 15000 |  | 15000 | 14818.75 | 98.79% | 14818.75 | 181.25 | 0 | 0 |  |  | 17500 | 17500
Accounting | 45000 | 0 | 45000 | 35027.68 | 77.84% | 35027.68 | 9972.32 | 0 | 0 |  |  | 50400 | 50400
Advisory Committees | 5000 | 0 | 5000 | 0 | 0% | 0 | 5000 | 2500 | 0 |  |  | 5000 | 5000
Insurance and bonds | 21000 | 0 | 21000 | 26009.33 | 123.9% | 26009.33 | -5009.33 | 0 | 0 |  |  | 30000 | 30000
Engineering Services | 132000 | 0 | 132000 | 137183.7 | 103.9% | 137183.7 | -5183.7 | 0 | 0 |  |  | 145000 | 145000
Legal Services | 108000 | 0 | 108000 | 122458.01 | 113.4% | 122458.01 | -14458.01 | 0 | 0 |  |  | 108000 | 108000
Manager Per Diem/Expense | 30000 | 0 | 30000 | 41190.18 | 137.3% | 41190.18 | -11190.18 | 0 | 0 |  |  | 42500 | 42500
Dues and Publications | 16000 | 0 | 16000 | 9159.66 | 57.25% | 9159.66 | 6840.34 | 2000 | 0 |  |  | 16000 | 16000
Office Cost | 191000 | 0 | 191000 | 150304.28 | 78.69% | 150304.28 | 40695.72 | 11000 | 0 |  |  | 256700 | 256700
Permit Review and Inspection | 160000 | 0 | 160000 | 197073.35 | 123.2% | 197073.35 | -37073.35 | 0 | 0 |  | 114000 | 117000 | 231000
Permit and Grant Database | 30000 | 0 | 30000 | 7047 | 23.49% | 7047 | 22953 | 0 | 0 |  |  | 31500 | 31500
Professional Services | 17400 | 0 | 17400 | 55058.14 | 316.4% | 55058.14 | -37658.14 | 0 | 0 |  |  | 36300 | 36300
Information Technology | 14400 |  |  |  |  | 0 | 0 | [5 empty] | 16800
Banking | 3000 |  |  |  |  | 0 | 0 | [5 empty] | 3500
Recording Services | 15500 | 0 | 15500 | 15495 | 99.97% | 15495 | 5 | 0 | 0 |  |  | 34800 | 34800
Staff Cost | 789681 | 0 | 789681 | 455344.88 | 57.66% | 455344.88 | 334336.12 | 180000 | 180000 |  |  | 596271.137 | 776271.137
Subtotal | 1575581 | 0 | 1575581 | 1266169.96 | 80.36% | 1266169.96 | 309411.04 | 195500 | 180000 | 0 | 114000 | 1498011.137 | 1792011.137
PROGRAMS AND PROJECTS
District Wide
10-yr Management Plan Update/Amendments | 80000 | 0 | 80000 | 15975.66 | 19.97% | 15975.66 | 64024.34 | 5000 | 5000 |  |  | 130000 | 135000
AIS Inspection and early response | 68000 | 0 | 68000 | 41901 | 61.62% | 41901 | 26099 | 18000 | 18000 |  |  | 50000 | 68000
Cost-share/Stewardship Grant | 260000 | 0 | 260000 | 206710.88 | 79.5% | 206710.88 | 53289.12 | 35000 | 35000 |  |  | 100000 | 280000
Data Collection and Monitoring | 213000 | 0 | 213000 | 185510.16 | 87.09% | 185510.16 | 27489.84 | 0 | 0 |  | 5000 | 228300 | 233300
Community Resiliency | 130000 | 0 | 130000 | 102240 | 78.65% | 102240 | 27760 | 0 | 0 |  |  | 260000 | 260000
Education and Outreach | 100000 | 0 | 100000 | 98143.96 | 98.14% | 98143.96 | 1856.04 | 9000 | 9000 |  |  | 101000 | 110000
Plant Restoration - U of M | 50000 | 0 | 50000 | 21931.65 | 43.86% | 21931.65 | 28068.35 | 0 | 0 |  |  | 54000 | 54000
Repair and Maintenance Fund | 100000 | 0 | 100000 | 12726.5 | 12.73% | 12726.5 | 87273.5 | 80000 | 80000 |  |  | 20000 | 100000
Wetland Management* | 157000 | 0 | 157000 | 6752.11 | 4.301% | 6752.11 | 150247.89 | 75000 | 75000 |  |  | 65000 | 140000
Groundwater Conservation* | 220000 | -49000 | 171000 | 40830.39 | 23.88% | 40830.39 | 130169.61 | 100000 | 100000 |  |  | 0 | 100000
Lake Vegetation Implementation | 76000 | 0 | 76000 | 76737.25 | 101% | 76737.25 | -737.25 | 7000 | 7000 |  |  | 141000 | 148000
Opportunity Project* | 250000 | 0 | 250000 | 0 | 0% | 0 | 250000 | 250000 | 250000 |  |  | 0 | 250000
Stormwater Ponds - U of M | 20000 | 0 | 20000 | 20000 | 100% | 20000 | 0 | 4830 | 4830 |  |  | 0 | 4830
Hennepin County Chloride Initiative | 90000 | 0 | 90000 | 93555.94 | 104% | 93555.94 | -3555.94 | 0 | 0 |  |  | 0 | 0
Lower Minnesota Chloride Cost-Share | 195000 | 0 | 195000 | 80684.95 | 41.38% | 80684.95 | 114315.05 | 0 | 0 |  |  | 0 | 0
Subtotal | 2009000 | -49000 | 1960000 | 1003700.45 | 51.21% | 1003700.45 | 956299.55 | 583830 | 583830 | 0 | 5000 | 1149300 | 1883130
Bluff Creek
Bluff Creek Tributary* | 5000 | 0 | 5000 | 4490.8 | 89.82% | 4490.8 | 509.2 | 2000 | 2000 |  |  | 3000 | 5000 | 0
Wetland Restoration at Pioneer | 478933 | 0 | 478933 | 92560.03 | 19.33% | 92560.03 | 386372.97 | 100000 | 100000 | 0 |  | 0 | 100000 | 350000
Bluff Creek B5 by Galpin | 120000 | 0 | 120000 | 13426.5 | 11.19% | 13426.5 | 106573.5 | 110000 | 110000 |  |  | 0 | 110000 | 614000
Subtotal | 603933 | 0 | 603933 | 110477.33 | 18.29% | 110477.33 | 493455.67 | 212000 | 212000 | 0 | 0 | 3000 | 215000
Riley Creek
Lake Riley - Alum Treatment* | 20000 | 0 | 20000 | 10717.5 | 53.59% | 10717.5 | 9282.5 | 0 | 0 |  |  | 0 | 0 | 300000
Rice Marsh Lake in-lake phosphorus load | 26000 | 0 | 26000 | 10717.5 | 41.22% | 10717.5 | 15282.5 | 15000 | 15000 |  |  | 0 | 15000 | 335000
Rice Marsh Lake Water Quality Improvement Phase 1 | 228000 | 0 | 228000 | 122993.81 | 53.94% | 122993.81 | 105006.19 | 20000 | 20000 |  |  | 7000 | 27000 | 300000
Riley Creek Restoration (Reach E and D3) | 78000 | 0 | 78000 | 20732.19 | 26.58% | 20732.19 | 57267.81 | 58000 | 58000 |  |  | 0 | 58000 | 700000
Upper Riley Creek Stabilization | 1447000 | 0 | 1447000 | 176347.53 | 12.19% | 176347.53 | 1270652.47 | 1267000 | 1267000 |  | 57000 | 600000 | 1924000 | 1625000
Middle Riley Creek | 61000 | 140000 | 201000 | 96775.29 | 48.15% | 96775.29 | 104224.71 | 27000 | 27000 |  |  | 0 | 27000 | 954000
St. Hubert Water Quality Project | 46000 | 0 | 46000 | 109.3 | 0.2376% | 109.3 | 45890.7 | 35000 | 35000 |  | 15000 | 0 | 50000 | 0
2023 Alum Application
LU-A1.10c
LU-A3.4
Subtotal | 1906000 | 140000 | 2046000 | 438393.12 | 21.43% | 438393.12 | 1607606.88 | 1422000 | 1422000 | 0 | 72000 | 607000 | 2101000
Purgatory Creek
Purgatory Creek Rec Area- Berm | 225000 | -91000 | 134000 |  | 0% | 0 | 134000 | 134000 | 134000 |  | 80000 | 0 | 214000 | 0
Lotus Lake in-lake phosphorus load control | 80000 | 0 | 80000 | 10717 | 13.4% | 10717 | 69283 | 65000 | 65000 |  |  | 50000 | 115000 | 690000
Silver Lake Water Quality BMP | 46000 | 0 | 46000 | 44402.83 | 96.53% | 44402.83 | 1597.17 | 0 | 0 |  |  | 9400 | 9400 | 535000
Administration | 4057.5 | 0 | 4057.5 |  | 0% | 0 | 4057.5 | 4058 | 4058 |  |  | 0 | 0 | 0
Scenic Heights | 4057.5 | 0 | 4057.5 |  | 0% | 0 | 4057.5 | 4058 | 4058 |  |  | 0 | 0 | 0
Hyland Lake in-lake phosphorus load control | 20000 | 0 | 20000 | 0 | 0% | 0 | 20000 | 20000 | 20000 |  |  | 0 | 0 | 320000
Duck Lake Watershed Load | 25000 | 0 | 25000 | 5149.48 | 20.6% | 5149.48 | 19850.52 | 15000 | 15000 |  |  | 0 | 15000 | 220000
Duck Lake Road Partnership | 235000 | 0 | 235000 | 235000 | 100% | 235000 | 0 | 0 | 0 |  |  | 235000 | 235000 | 0
Lotus Lake Watershed Improvement Project (LL_1,3,7, & 8) | 325000 | 0 | 325000 | 21654.25 | 6.663% | 21654.25 | 303345.75 | 255000 | 255000 |  |  | 95000 | 350000 | 1304000
Subtotal | 960057.5 | -91000 | 869057.5 | 316923.56 | 36% | 316923.56 | 552133.94 | 493058 | 493058 | 0 | 80000 | 469400 | 1018400 | 3069000
Reserve | 230000 |  | 230000 | 0 | 0% | 0 | 230000 | 230000 | 230000 |  |  | 95000 | 325000
TOTAL EXPENDITURE | 7284571.5 | 0 | 7284571.5 | 3135664.42 | 43.05% | 3135664.42 | 4148907.08 | 3136388 | 3120888 | 0 | 271000 | 3821711.137 | 7334541.137 | 3069000
EXCESS REVENUES OVER (UNDER) EXPENDITURES | 110000 | 0 | 110000 |  |  |  | 110000 |  |  |  |  | 0 | -105442 | -3069000
*Denotes Multi-Year Project - See Table 2 for details | [10 empty] | % Change | 4.975% | 0.686%
[8 empty] | 1012519.08 |  |  |  | 2022 levy $3.6M | 2022 budg $7.2M
2023 YEAR END SUMMARY
Items | Revised 2022 Budget | Actual Spent (Recvd) Year-to-Date | End of Year Remaining | Projected End of Year Remaining | Projected Carry Over Budget
REVENUES
Plan Implementation Levy | 3640581 |  |  | 0 | 0
Permit | 25000 | 106956.05 | -81956.05 | 0 | 0
Grant Income | 71933 | 72875 | -942 | 0 | 0
Investment Income | 30000 | 36267.83 | -6267.83 | 0 | 0
Past Levies (Carry Overs) | 3355057.5 |  |  | 0 | 3136388
Miscellaneous Income | 0 |  |  | 0 | 0
Reimbursements | 0 |  |  | 0 | 0
Partner Funds | 272000 |  |  | 0 | 0
TOTAL REVENUE | 7394571.5 | 216098.88 | 7178472.62 | 0 | 3136388
EXPENDITURES
Administration
Audit | 15000 | 14818.75 | 181.25 | 0 | 0
Accounting | 45000 | 35027.68 | 9972.32 | 0 | 0
Advisory Committees | 5000 | 0 | 5000 | 2500 | 0 | Due to covid and meeting remotely, no expenditure was required.
Insurance and bonds | 21000 | 26009.33 | -5009.33 | 0 | 0 | A more detailed inventory of the data collection and office equipment resulted in a higher valuation of assets.
Engineering Services | 132000 | 137183.7 | -5183.7 | 0 | 0
Legal Services | 108000 | 122458.01 | -14458.01 | 0 | 0 | Lawsuit, hostile work environment investigation, and data requests account for unaticipated expenditures
Manager Per Diem/Expense | 30000 | 41190.18 | -11190.18 | 0 | 0 | Five months had either a continuance of a board meeting or a special meeting. There were 4 GC, and 3 PC meetings as well. Other unanticipated costs were web page and GC manual review per diem requests.
Dues and Publications | 16000 | 9159.66 | 6840.34 | 2000 | 0 | RPBCWD did not renew membership in the Center for Watershed Protection and the NALMS membership was reduced from two members to one.
Office Cost | 191000 | 150304.28 | 40695.72 | 11000 | 0 | Reduction in printing costs as a result of online board packets and electronic submittals.
Permit Review and Inspection | 160000 | 197073.35 | -37073.35 | 0 | 0 | 24 of the 79 applications submitted in 2022 came from government agencies so no fees were collected.
Permit and Grant Database | 30000 | 7047 | 22953 | 0 | 0 | Work is in-progress. Much of the grants database ground work was performed by the communications manager thus reducing the time HEI had to dedicate to the database development.
Professional Services | 17400 | 55058.14 | -37658.14 | 0 | 0 | Hostile work environment investigation and the hiring of Drown Assoc HR firm for recruitment and hiring of admnistrator
Recording Services | 15500 | 15495 | 5 | 0 | 0
Staff Cost | 789681 | 455344.88 | 334336.12 | 180000 | 180000 | Much of this was carried over as balance from preceeding year. In addition, there were two fewer fulltime employees and those that assumed new positions were paid at a discounted rate from their predecessors. Interns did not start until later in the season than anticipated and left earlier than anticipated. Two fewer interns were hired than anticipated. Our contract employee left early to take another position. Health insurance premiums were reduced as a result of staff turnover and a change in health care plan.
Subtotal | 1575581 | 1266169.96 | 309411.04 | 195500 | 180000
PROGRAMS AND PROJECTS
Items | Revised 2022 Budget | Actual Spent (Recvd) Year-to-Date | End of Year Remaining | Projected End of Year Remaining | Projected Carry Over Budget
District Wide
10-yr Management Plan Update/Amendments | 80000 | 15975.66 | 64024.34 | 5000 | 5000 | Priorities changed to an Ecological Health Action Plan. Costs defered until later years. Budget increase in 2023
AIS Inspection and early response | 68000 | 41901 | 26099 | 18000 | 18000 | Eden Prairie sent invoice on 1/31/23 this balance will zero out
Cost-share/Stewardship Grant | 260000 | 206710.88 | 53289.12 | 35000 | 35000 | Shorewood has not yet submitted a request for payment on their sump manholes and SAFL baffles.
Data Collection and Monitoring | 213000 | 185510.16 | 27489.84 | 0 | 0
Community Resiliency | 130000 | 102240 | 27760 | 0 | 0 | Model built. Finall comments being received from EP. Will present at upcoming workshop. March or April.
Education and Outreach | 100000 | 98143.96 | 1856.04 | 9000 | 9000
Plant Restoration - U of M | 50000 | 21931.65 | 28068.35 | 0 | 0 | Invoice received afer the February 1 deadline. This will zero out.
Repair and Maintenance Fund | 100000 | 12726.5 | 87273.5 | 80000 | 80000 | Work on Lake Susan Park Pond reuse system was delayed. Funds dedictaed in 2023
Wetland Management* | 157000 | 6752.11 | 150247.89 | 75000 | 75000 | Did not construct the strawman model. Field assessments to be finished this year and work on model to occur in 2023.
Groundwater Conservation* | 171000 | 40830.39 | 130169.61 | 100000 | 100000 | No work done. Other projects prioritized.
Lake Vegetation Implementation | 76000 | 76737.25 | -737.25 | 7000 | 7000
Opportunity Project* | 250000 | 0 | 250000 | 250000 | 250000 | No opportunity projects were identified for 2022
Stormwater Ponds - U of M | 20000 | 20000 | 0 | 4830 | 4830
Hennepin County Chloride Initiative | 90000 | 93555.94 | -3555.94 | 0 | 0 | The orginal 2022 budget should have $105,000 not the $90K shown. All funds are reimburseable through WIBF grant.
Lower Minnesota Chloride Cost-Share | 195000 | 80684.95 | 114315.05 | 0 | 0 | This partnership between LMRWD, RBWMO, and RPBCWD did not get adequate applicants to utilize the entire fund. All three organizations reached out to all parks departments, all PW departments, all school districts, and as many private contractors as we had contact informaiton for.
Subtotal | 1960000 | 1003700.45 | 956299.55 | 583830 | 583830
Bluff Creek
Bluff Creek Tributary* | 5000 | 4490.8 | 509.2 | 2000 | 2000 | Subtantially complete
Wetland Restoration at Pioneer | 478933 | 92560.03 | 386372.97 | 100000 | 100000 | RPBCWD had one less property to purchase as Chanhassen made that purchase.
Bluff Creek B5 by Galpin | 120000 | 13426.5 | 106573.5 | 110000 | 110000 | Project delayed to 2023/24 to better align with Chanhassen proposed road project
Subtotal | 603933 | 110477.33 | 493455.67 | 212000 | 212000
Items | Revised 2022 Budget | Actual Spent (Recvd) Year-to-Date | End of Year Remaining | Projected End of Year Remaining | Projected Carry Over Budget
Riley Creek
Lake Riley - Alum Treatment* | 20000 | 10717.5 | 9282.5 | 0 | 0 | Sedimnet anaylis performed in 2022. Will guide future treatment.
Rice Marsh Lake in-lake phosphorus load | 26000 | 10717.5 | 15282.5 | 15000 | 15000 | One additional treatment in coming year
Rice Marsh Lake Water Quality Improvement Phase 1 | 228000 | 122993.81 | 105006.19 | 20000 | 20000
Riley Creek Restoration (Reach E and D3) | 78000 | 20732.19 | 57267.81 | 58000 | 58000 | Design phase.
Upper Riley Creek Stabilization | 1447000 | 176347.53 | 1270652.47 | 1267000 | 1267000 | To be bid in 2023 for fall winter 2023-24 construction
Middle Riley Creek | 201000 | 96775.29 | 104224.71 | 27000 | 27000
St. Hubert Water Quality Project | 46000 | 109.3 | 45890.7 | 35000 | 35000 | One additional pay app on March 1 meeting and ongoing vegetation maintenance
2023 Alum Application
LU-A1.10c
LU-A3.4
Subtotal | 2046000 | 438393.12 | 1607606.88 | 1422000 | 1422000
Purgatory Creek
Purgatory Creek Rec Area- Berm | 134000 |  | 134000 | 134000 | 134000 | Do not have capacity to manage project. Have spoken with EP to see if they can manage the project.
Lotus Lake in-lake phosphorus load control | 80000 | 10717 | 69283 | 65000 | 65000 | Alum dose in 2023
Silver Lake Water Quality BMP | 46000 | 44402.83 | 1597.17 | 0 | 0 | Substantially complete
Scenic Heights | 4057.5 |  | 4057.5 | 4058 | 4058 | Substantially complete
Hyland Lake in-lake phosphorus load control | 20000 | 0 | 20000 | 20000 | 20000 | Three rivers took over project. Funds were reserved there in case they requested help.
Duck Lake Watershed Load | 25000 | 5149.48 | 19850.52 | 15000 | 15000 | Substantially complete
Duck Lake Road Partnership | 235000 | 235000 | 0 | 0 | 0
Lotus Lake Watershed Improvement Project (LL_1,3,7, & 8) | 325000 | 21654.25 | 303345.75 | 255000 | 255000 | Still in concept phase.
Subtotal | 869057.5 | 316923.56 | 552133.94 | 493058 | 493058
Reserve | 230000 | 0 | 230000 | 230000 | 230000
TOTAL EXPENDITURE | 7284571.5 | 3135664.42 | 4148907.08 | 3136388 | 3120888
EXCESS REVENUES OVER (UNDER) EXPENDITURES | 110000 |  | 110000